## Sheet1
项目名称: Project Name： | [6 empty] | 项目交付保障方案 Project Delivery Assurance Plan
客户： Customer ： | [6 empty] | 项目号： Project Number： |  |  |  | 项目经理： Project Manager
保障方案Assurance Planning: | [12 empty] | 项目类型 Project Category | [7 empty] | COM：技术委员会 FD：职能部门总监 DD：板块总监/分公司总经理 DH：专业室主任 PM：项目经理 PFM：项目其他管理职务 PDL：项目专业负责人
此保障计划活动从项目起始开始执行，是执行项目交付保障活动的最低要求。 This Assurance Activity plan is provided as a starting point for our projects. Assurance activities planning is the minimum requirement for ensuring project delivery.
项目交付保障部门负责确认保障活动计划的具体内容，确保活动的执行及鉴定。 The project delivery support department is responsible for confirming the plan, ensuring the execution and evaluation of the activity.
| 非预期（在项目需要时执行） Not Expected (to be performanced if necessary for the project) | [8 empty] | 一类 (Cat C)：<=50万，小型设计及咨询项目Small-scale design and consulting projects |  |  |  |  | COM | FD | DD | DH | PM | PDL | ● Responsible Party ● Accountable Party ● Consulted Party ● Informed Party
| 建议（这些活动是建议的，并应在项目需要时进行） Recommended (these activities are recommended and shall be undertaken as necessary for the project) | [8 empty] | 二类 (Cat B)：>50万，<=500万，设计及咨询 design and consulting projects
| 必须（如果这些活动与项目范围相关，则应进行） Expected (these activities shall be performed if relevant to the scope of the project) | [8 empty] | 三类 (Cat A)：>500万，设计及咨询项目 design and consulting projects；EPC（包含EP、EPCm）
保障方案活动 Assurance Planning Activitiy:
No. | 保障活动 Assurance Activity |  | 适用性 Applicable |  |  | 关注点 Focus |  | 计划日期： Date Planned | 参考文件 Reference Document | 保障活动输出（包括报告等） Assurace Outcomes (incl Report etc.) |  | 活动开始 Actions Open |  | 活动结束 Actions Closed
1 | 项目分类 Project Categorisation |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 绩效 Performance |  | 项目识别阶段 Identification | ACC-PRO-110144 PCS-STD-110001 SW-PS-BA00-REG-001C-2020 | 三类项目的项目合同风险分类表 Cat A：ProjectContract Risk Categorisation Form |  |  |  |  | ●C | ●I | ●A | ●C | ●R
2 | 人员配备计划和个人能力评估 Staffing Plan & Personmal Competency Review |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 能力 Competence |  | 项目识别阶段 Identification | SW-PS-BA00-POL-001C-2020 CHN-HRM-PRO-900015 CHN-HRM-PRO-900016 CHN-PMG-PRO-900002 CHN-PMG-PRO-900009 | 人员计划 staff plan |  |  |  |  | ●C |  | ●R | ●A
3 | 商务交接 BD Handover | BD Handover PEER Review | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 执行的连续性 Continuity of Execution |  | 项目启动的14天内 Within 14 days of Project Start | CSV-POL-110019 CHN-CSV-STD-900002 CHN-PMG-PRO-900003 CHN-PMG-FOR-900002 CHN-PMG-FOR-900003 CHN-PMG-FOR-900007 | 纪要记录/行动项 Review Minutes/action list | [5 empty] | ●I |  | ●I | ●A
4 | 项目内部检查 Internal Project Reviews |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 绩效 Performance |  | 至少每月一次 at least Monthly | PCS-MAN-110001 PCS-TEM-110001 CHN-PMG-FOR-900005 CHN-PMG-FOR-900006 | 月报报告，行动项 PMR report, action list | [7 empty] | ●C | ●A | ●R
5 | 项目质量审查/评估 Project Quality Audits/Assessments |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 一致性及绩效 Conformance & Performance |  | 项目执行阶段 Process stages | QUA-POL-100003 QUA-STD-100003 CHN-QUA-STD-100003 CHN-OPA-PRO-900003 CHN-OPA-TEM-110001 CHN-OPA-TEM-110002 CHN-PMG-PRO-900005 CHN-PMG-TEM-900001 | 审查报告/检查表/行动项 Audit report/checklist/action list 纪要记录 Review Minutes |  |  |  |  | ●C | ●I |  | ●R | ●A | ●R
6 | 项目风险管理检查 Project Risk Management Review | Risk Management Review - Spot check | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 及时性 Timeliness |  | 适当时间 Appropriate points | ACC-STD-100001 ACC-STD-100002 PCS-PCM-110003 PCS-STD-110001 CHN-HSE-PRO-900001 | 项目风险登记表 Project Risk Register |  |  |  |  | ●C | ●I | ●I | ●C | ●A | ●R
7 | 客户满意度 Customer Satisfaction |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 绩效表现和满意度 Performance & Satisfaction |  | 每6个月 Every 6 months | CHN-CSV-PRO-900001 | 反馈报告/满意度调查表 feedback report/QR | [5 empty] | ●A |  | ●I
8 | 经验教训 Lesson Learn |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 持续改进 Continuous Improvement |  | 适当时间 Appropriate points | PMG-PRO-110131 CHN-PMG-PRO-900007 | 经验教训总结表 Lesson Learned Capture Sheet 设计完工报告 Design completion report | [5 empty] | ●I | ●A | ●C | ●R
9 | 变更管理 Management of Change - 抽查Spot check | Management of Change - Spot check | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 一致性 Conformance |  | 适当时间 Appropriate points | PCS-PCM-110004 SW-PS-DA00-REG-011C CHN-ENG-FOR-900042 CHN-ENG-FOR-900043 | 项目变更登记表 Project Change Registration Form | [5 empty] | ●I |  | ●C | ●A | ●R
10 | 特殊项目交付内容 Specific Project Delivery Objectives (SPDO's) | Specific Project Delivery Objectives (SPDO's) | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 绩效表现和满意度 Performance & Satisfaction |  | 适当时间 Appropriate points | CONTRACT/Deal | 项目交付物 Project Delivery Objectives | [7 empty] | ●C | ●A | ●R
11 | 项目安全审查 Project HSSE Audits | HSSE Audits | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 一致性及绩效 Conformance & Performance |  | 适当时间 Appropriate points | HSE-POL-100001 HSE-STD-100063 CHN-OPA-PRO-900002 SW-PS-S120-REG-205C-2020 CHN-OPA-PRO-900003 CHN-OPA-TEM-110001 CHN-OPA-TEM-110002 | 审查报告/检查表/行动项 Audit report/checklist/action list | [5 empty] | ●I |  | ●I | ●A | ●R
12 | 同行审查 PEER Reviews - 执行及技术 Execution & Technical | PEER Reviews - Execution & Technical | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 一致性及绩效 Conformance & Performance |  | 适当时间 Appropriate points | CHN-OPA-PRO-900003 CHN-PMG-PRO-900006 CHN-PMG-FOR-900008 | 记录纪要/行动项 Review report/action list |  |  |  |  | ●I | ●C | ●A | ●I | ●R
13 | 项目质量审查/评估 Project Quality Audits/Assessments |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 一致性及绩效 Conformance & Performance |  | 产品阶段 Product stages | QUA-POL-100003 QUA-STD-100003 CHN-QUA-STD-100003 CHN-OPA-PRO-900003 CHN-OPA-TEM-110001 CHN-OPA-TEM-110002 | 审查报告/检查表/行动项 Audit report/checklist/action list 纪要记录 Review Minutes |  |  |  |  | ●C | ●I |  | ●R | ●A
14 | 特殊目标审查 Special Purpose Reviews | Special Purpose Reviews | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 基于风险的绩效 Risk Based Performance |  | 适当时间 Appropriate points | CONTRACT/Deal | 纪要记录 Review Minutes | [7 empty] | ●A |  | ●R
15 | 职能审核/评估 Business Functional Audits/ Assessments | Business Functional Audits/ Assessments | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 一致性 Conformance |  | 适当时间 Appropriate points | CHN-OPA-PRO-900003 CHN-OPA-TEM-110001 CHN-OPA-TEM-110002 CHN-PMG-PRO-900008 | 审查报告/检查表/行动项 Audit report/checklist/action list |  |  |  |  | ●C | ●R | ●A | ●I
研讨会&评审 Workshops & Reviews:
No. | 描述 Description |  | 适用性 Applicable |  |  | 关注点 Focus |  | 计划日期： Date Planned | 参考文件 Reference Document | 保障活动输出（包括报告等） Assurace Outcomes (incl Report etc.) |  | 活动开始 Actions Open |  | 活动结束 Actions Closed
1 | HAZOP/HAZID审查 HAZOP/HAZID Reviews |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  | SW-PS-DA00-REG-006C-2020 | HAZOP 报告 HAZOP report |  |  |  |  | ●C |  | ●I | ●C | ●A | ●R
2 | P&ID/UID审查 P&ID/UID Review |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  | SW-TS-DC00-SPC-001C-2020 SW-PS-S410-REG-001C-2020 | 纪要记录 Review Minutes |  |  |  |  | ●C |  | ●I | ●C | ●A | ●R
3 | 防爆区域设置审查 Explosion-proof Arae Division Review |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  | SW-PS-S450-REG-003C-2019 | 纪要记录 Review Minutes |  |  |  |  | ●C |  | ●I | ●C | ●A | ●R
4 | 总图审查 General Plot Plan Review |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  | SW-PS-S470-REG-004C-2019 | 纪要记录 Review Minutes |  |  |  |  | ●C |  | ●I | ●C | ●A | ●R
5 | 概算审查 Cost Estimate Review |  | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 费用 Cost |  |  | CHN-ENG-PRO-900003 | 纪要记录 Review Minutes | [6 empty] | ●I | ●C | ●A | ●R
6 | 可操作性评审 Operability Reviews | Operability Reviews | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  |  | 纪要记录 Review Minutes | [7 empty] | ●C | ●A | ●R
7 | 可维护性评审 Maintainability Reviews | Maintainability Reviews | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  |  | 纪要记录 Review Minutes | [7 empty] | ●C | ●A | ●R
8 | 可施工性审查 Constructabilty Review | Constructabilty Review | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) | 技术 Technicle |  |  | CHN-CON-PRO-900003 CHN-CON-FOR-900007 | 可施工性审查检查表 Constructability Review Checklist | [7 empty] | ●C | ●A | ●R
9 | 价值工程 Value Engineering | Value Engineering | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A) |  |  |  | PCS-GDS-110016(Singapore) | 价值工程学习报告 Value Engineering Study report | [7 empty] | ●A
10 | 计划发展 Schedule Development | Schedule Development | 一类 (Cat C) | 二类 (Cat B) | 三类 (Cat A)
关注点/Concerns:

## Sheet2
项目交付保障方案责任矩阵
No. | 保障活动 Assurance Activity |  |  | TCOM | FD | BDD | DH | PM | PDL
1 | 项目分类 Project Categorisation |  |  | ●C | ●I | ●A | ●C | ●R
2 | 人员配备计划和个人能力评估 Staffing Plan & Personmal Competency Review |  |  | ●A |  | ●C | ●R
3 | 商务交接 BD Handover |  | BD Handover PEER Review | ●I | ●A |  | ●I | ●R
4 | 项目内部检查 Internal Project Reviews |  |  |  |  | ●A | ●C | ●R
5 | 项目质量审查/评估 Project Quality Audits/Assessments |  |  | ●A | ●C | ●I | ●R
6 | 项目风险管理检查 Project Risk Management Review |  | Risk Management Review - Spot check | ●C | ●I | ●A | ●C | ●R
7 | 客户满意度 Customer Satisfaction |  |  |  | ●A | ●R | ●I
8 | 经验教训 Lesson Learn |  |  |  | ●I | ●A | ●C | ●R
9 | 变更管理 Management of Change - 抽查Spot check |  | Management of Change - Spot check | ●C |  | ●A | ●R
10 | 特殊项目交付内容 Specific Project Delivery Objectives (SPDO's) |  | Specific Project Delivery Objectives (SPDO's) |  |  |  | ●A | ●R | ●C
11 | 项目安全审查 Project HSSE Audits |  | HSSE Audits |  | ●I | ●A | ●C | ●R
12 | 同行审查 PEER Reviews - 执行及技术 Execution & Technical |  | PEER Reviews - Execution & Technical | ●I | ●C | ●A | ●I | ●R
13 | 项目质量审查/评估 Project Quality Audits/Assessments |  |  | ●A | ●C | ●I | ●R
14 | 特殊目标审查 Special Purpose Reviews |  | Special Purpose Reviews |  |  |  | ●A |  | ●R
15 | 职能审核/评估 Business Functional Audits/ Assessments |  | Business Functional Audits/ Assessments | ●C | ●R | ●A | ●I
No. | 研讨会&评审 Workshops & Reviews: |  |  | TCOM | FD | BDD | DH | PM | PDL
1 | HAZOP/HAZID审查 HAZOP/HAZID Reviews |  |  | ●A | ●I | ●C | ●R
2 | P&ID/UID审查 P&ID/UID Review |  |  | ●A | ●I | ●C | ●R
3 | 防爆区域设置审查 Explosion-proof Arae Division Review |  |  | ●A | ●I | ●C | ●R
4 | 总图审查 General Plot Plan Review |  |  | ●A | ●I | ●C | ●R
5 | 概算审查 Cost Estimate Review |  |  | ●A | ●I | ●C | ●R
6 | 可操作性评审 Operability Reviews |  | Operability Reviews | ●A | ●I | ●C | ●R
7 | 可维护性评审 Maintainability Reviews |  | Maintainability Reviews | ●A | ●I | ●C | ●R
8 | 可施工性审查 Constructabilty Review |  | Constructabilty Review | ●A | ●I | ●C | ●R
9 | 价值工程 Value Engineering |  | Value Engineering | ●A | ●I | ●C | ●R
10 | 计划发展 Schedule Development |  | Schedule Development | ●A | ●I | ●C | ●R